## Slide 1: Unit 9: Program Evaluation
CERT Program Manager

## Slide 2: Unit Objectives
At the conclusion of this unit, the participants will be able to develop a process for evaluating a local CERT program:
  Explain what program evaluation is
  Describe the purpose of evaluating a program
  List the steps for evaluating various program components
  Identify the characteristics of a Program Report
CERT Program Manager: Program Evaluation
PM 9-1

## Slide 3: Unit Topics
What Program Evaluation Is
Why Do Program Evaluation
How to Do Program Evaluation
Program Report
CERT Program Manager: Program Evaluation
PM 9-1

## Slide 4: Program Evaluation
What happens during a program evaluation?
  Program evaluation is an ongoing process that asks (and answers) three questions:
    What are we doing now?
    How well are we doing it?
    Do we need to do something differently? If so, what?
  Document findings in Program Report
PM 9-2

## Slide 5: Goals and Objectives – Unit 2
Objectives specify activities to accomplish goal
During program evaluation, Program Manager needs to find out:
  How well program is meeting objectives
  What corrections, if any, are needed
PM 9-2

## Slide 6: Why? Evaluate Performance
Evaluation ensures consistency in day-to-day operational activities
By asking “How well are we doing?” the Program Manager:
  Scrutinizes program’s accomplishments
  Verifies that accomplishments meet standards program has set
CERT Program Manager: Program Evaluation
9-6
PM 9-3

## Slide 7: Why? Maintain Program Control
Evaluation reassures State and local officials that volunteers are well trained and supervised
  Evaluation reduces and manages the instances of independent or undirected volunteer actions
By asking “Do we need to do something differently?” the Program Manager is able to make adjustments as needed
CERT Program Manager: Program Evaluation
PM 9-3

## Slide 8: Program Evaluation Process
Decide what you want to learn
Figure out strategy for collecting information
Collect information
Analyze information you collect and decide on next steps
CERT Program Manager: Program Evaluation
PM 9-4

## Slide 9: #1: What You Want to Learn
How WELL did we achieve our objectives?
PM 9-4

## Slide 10: SMART
What elements make an effective objective?
  Specific
  Measurable
  Achievable
  Relevant
  Time Bound
PM 9-4

## Slide 11: Program Components
Think about your own CERT program
What are some specific program elements that should be evaluated?
  CERT Basic Training
  Other training
  Program: volunteers, resources, funding
  Exercises and drills conducted
  Community activities
  CERT partners who support program
PM 9-5

## Slide 12: #2: Evaluation Strategy
Who needs information being collected?
What types of data are needed?
Where will it be found?
Sample Objective
    To support a community’s public safety efforts by providing CERT members whenever requested
PM 9-5

## Slide 13: Activity
Determining Whether or Not Your Program’s Performance Is Meeting Your Goals
CERT Program Manager: Program Evaluation
PM 9-8

## Slide 14: #3: Collect Data
PM 9-9

## Slide 15: #4: Analyze Data; Take Action
Review of evaluation goals
  What do I want to learn?
Compare results you got to what you expected to get
Consider options
Take corrective action if needed
PM 9-9

## Slide 16: Program Report
Program Report documents evaluation results
  Justify your conclusions or recommendations using your data findings
  Translate recommendations into specific action plans: who, what, when, how, and any other “need-to-know” specifics
  Level and scope of content depend on recipient of report
    Be mindful of intended audiences
  Keep Program Report concise
PM 9-10

## Slide 17: Activity
Creating a Program Report
CERT Program Manager: Program Evaluation
PM 9-10

## Slide 18: Unit Summary
The importance of evaluating a CERT program
What to evaluate in a CERT program and how to do it
Creating a Program Report
CERT Program Manager: Program Evaluation
PM 9-12